## Tasks
No. | Subjects | Assign to | Start | End | Real | Status | Diffculity | Comments
1 | Xóa bỏ thông báo khi đăng nhập thành công | Bang | 2013-12-16 | 2013-12-16 | 2013-12-16 | Finished | Easy
2 | Hoàn thành các giao diện còn thiếu(3 form NguyenMauPT, PhuongTien,VanHanh | Bang | 2013-12-16 | 2013-12-17 | 2013-12-17 | Finished | Easy
3 | Đổi tên các control trên form… nút bấm , dataview … | Bang | 2013-12-16 | 2013-12-17 | 2013-12-17 | Finished | Easy
4 | Chỉnh form ra giữa màn hình,đổi tiêu đề form, chọn cả dòng | Bang | 2013-12-17 | 2013-12-17 |  | Working | Easy
5 | From DonViQuanLy | Bang | 2013-12-17 | 2013-12-18 |  | Working | Medium | anh xem lại cái chức năng delete của em , thêm nữa là : những bản ghi em thêm trc khi anh sửa code của em ko sửa và xóa dc ạ, nó hiện lên ràng buộc khóa j đấy
6 | From DonViTC | Bang | 2013-12-18 | 2013-12-19 |  | Pending | Medium
7 | NhanVien | Bang | 2013-12-19 | 2013-12-20 |  | Pending | Medium
8 | NguyenMauPhuongTien | Bang | 2013-12-20 | 2013-12-21 |  | Pending | Medium
9 | PhuongTien + AutoNum =tự tăng, do cơ sở dữ liệu quy đinh. + PhuonTienID = AutoNum+ MaLoai_PT +LanTieuTu….. | Bang | 2013-12-21 | 2013-12-23 |  | Pending | Diffculity
10 | VanHanh + ID tự tăng VH+autoNumber + Chưa rõ về ca làm việc | Bang | 2013-12-22 | 2013-12-25 |  | Pending | Diffculity
11
12
13
14
15
16

## Reference
Status | Diffculity | Member
Pending | Very Diffculity | NDQuang
Working | Diffculity | Bang
Finished | Medium | All
Closed | Easy
Review | Not Defined